## Requirement
Req ID | Description | Status | Phase | Priority
1 | Membership can also be store wise | Closed | Phase 2 | Medium
2 | Offers will definitely will eb store wise | Closed | MVP | Critical
3 | Add Three fields with every Benefit viz. Product, Retail Price, cost | Closed | MVP | High
4 | Add a AI ability to be able to auto fill branding information for clients searching in the web about the company details as a start up for the business | Open | Phase 2 | Medium
5 | A staff can be associated with multiple stores though they can have a primary store. They can log in from any of the stores and should be able to login so that any activity he/she does is associated with that stores. This should by itself be taken care of as every staff will login to the terminal at the store however we need to have the facility for them to choose the stores in case they are using mobile( phase 2) | Closed | MVP | Critical
6 | Staff has the mobile app | Closed | Phase 2 | Medium
7 | Provide facility for Upgrade of Membership from Silver to Gold - Platninum, Caluate the new cost on pro rata basis but reset the subscription period basedon that tier period/duration | Open | Phase 2 | High
8 | Add an approval workflow for the Org admin changes specially Membership/Offers by the owner or specific designated entity. | Open | Phase 2 | High
9 | When Customer logs out, URL lands on Org path | Closed
10 | Sign out is not available easily - not an issue for customers if they are using App But for future reference | Open
11 | tax is not calculated when purchased subscription | Closed
12 | I tried adding staff with duplicate phone number , it didnt give me any error message | Open
13 | Staff is saving without name - Critical issue | Closed
14 | It is working but I think flow is duplicate for saving | Open
15 | Not all business shown in the business discovery | Closed
16 | Membership Edit save is not working | Closed
17 | No duplicate Business organization onboarding check | Open |  | Low
18 | Add Duplicate Org Admin, Overriding the details if he/she already exists | Closed |  | Medium
19 | Effective date from and to is timestamp and text field ( should be date field and have calender attached) | Closed |  | Low
20 | Country region cities ref data is not being fetched from database | Closed |  | Critical
21 | User and Access screen - no edit button available for new org created by client - available for existing customer only view so not able to set counter operation for org admins. | Open |  | Low
22 | Benefits -- Multiple product option setting is not working. In the UI multiple products gets selected but when saved it saves only one product id in the DB, it doesn’t show the products on the sumary table on the benfits screen. Interesting when open the benefits in edit mode it still has all the 3 products selected. | Open |  | Critical
23 | Products at benefits level is not available foe view by the customer on benefits summary is | Open |  | Critical
24 | The same issue with display of multiple products option mapped to an offer, summary displays all the products linked at th esummary here. Where are the mappings stored? | Open |  | Critical
25 | Product catalog set up for a new org, the current set up process is not well documented even if it is via DB set up, also add a facility to add these mappings online by upload of excel feature, This is even more important as the org admin is not at all aware of what needs to be done it also involved creation of the integration row which is further down in the set up. | Open |  | Critical
26 | Remove/hide indvidual component previews from the screen as it creates confusion with org admin we can renable/view once they are implemented. We can keep just the benefits preview as it is not available until it is added to a membership. | Open |  | Medium