## W37-W65 Tracker
MEMGINE ¦ Poynt Collect — Remote Customer E2E Tests
Unit tests: reported completed by Codex (not independently verified here). Integration/browser outcomes are tracked separately.
Total scenarios | 29 | Integration passed | 1 | Integration pending | 28 | Integration failed | 0
Test ID | Scenario | Expected result | Test method | Original status | Test execution type | Existing unit coverage (baseline) | Completion / remaining validation | Integration / browser status
W37 | Normal payment approval | PROCESSING → SUCCEEDED | Real Test Lab payment | Passed | Unit + Browser Manual | Partial - Captured SALE provider test exists | Prior real payment passed; confirm customer-to-subscription E2E evidence | Passed
W38 | Delayed response (5–15 seconds) | Processing remains visible; success follows | Controlled delayed provider response | Pending | Unit + Browser Simulation | Missing - Delayed response test | Unit PASS (reported); browser/manual simulation PENDING | Not started
W39 | Long delay (30–60 seconds) | No premature failure or attention warning | Controlled delayed response | Pending | Unit + Browser Simulation | Missing - Long delay test | Unit PASS (reported); browser/manual simulation PENDING | Not started
W40 | Repeated PROCESSING responses | Read-only status polling continues | Controlled API response sequence | Pending | Unit + Integration | Missing - Repeated PROCESSING polling test | Unit PASS (reported); DEV integration PENDING | Not started
W41 | Captured payment, response lost | Read-only reconciliation recovers SUCCEEDED | Existing captured transaction verified | Passed | Unit + Integration | Covered - Read-only reconciliation test | Previously marked Passed; confirm DEV recovery evidence / reconciliation | Not started
W42 | Temporary status API failure | Original intent preserved; recovery available | Simulated GET error | Pending | Unit + Integration | Missing - Temporary status API failure test | Unit PASS (reported); DEV integration PENDING | Not started
W43 | Polling reaches timeout | Uncertain status; manual recheck; no retry | Controlled timeout | Pending | Unit + Browser Simulation | Missing - Polling timeout test | Unit PASS (reported); browser/manual simulation PENDING | Not started
W44 | Success after polling timeout | Manual recheck detects success | Delayed success simulation | Pending | Integration + Browser Simulation | Missing - Success after timeout test | Unit PASS (reported); DEV integration + browser PENDING | Not started
W45 | Browser refresh during processing | Existing payment recovered | Browser test with controlled delay | Pending | Browser Manual | Missing - Browser refresh recovery test | Browser manual PENDING | Not started
W46 | Browser tab closed during processing | Recovery after reopening/login | Browser test with controlled delay | Pending | Browser Manual | Missing - Browser tab closure recovery test | Browser manual PENDING | Not started
W47 | Browser Back during processing | No second charge | Browser navigation test | Pending | Browser Manual | Missing - Browser Back navigation test | Browser manual PENDING | Not started
W48 | Duplicate confirmation requests | At most one charge and one subscription | Concurrency / API test | Pending | Integration | Covered - Concurrent confirmation test | Unit PASS (reported, if applicable); DEV integration PENDING | Not started
W49 | Poynt transaction not found | Unresolved; no false failure | Mocked GET lookup | Pending | Unit | Partial - Transaction lookup uncertainty test | Unit PASS (per yesterday’s Codex report; verify test results) — no live integration required | Not started
W50 | Wrong transaction or amount | Cannot finalize payment | Mocked mismatched response | Pending | Unit | Covered - Transaction and amount mismatch tests | Unit PASS (per yesterday’s Codex report; verify test results) — no live integration required | Not started
W51 | Captured, activation pending | Payment received; no false success of activation | Simulated delayed finalization | Pending | Unit + Integration | Partial - Subscription finalization test | Unit PASS (reported); DEV integration PENDING | Not started
W52 | Definitive payment decline | FAILED; no subscription created | Provider-supported decline scenario | Pending | Unit + Integration + Browser Manual | Partial - Definitive decline test; verify fixture | Unit PASS (reported); DEV integration + browser PENDING | Not started
W53 | Concurrent status checks | Single finalization; no duplicate subscription | Parallel GET integration test | Pending | Integration | Missing - Concurrent status GET test | Unit PASS (reported, if applicable); DEV integration PENDING | Not started
W54 | Google Pay cancelled before authorization | No charge; original checkout remains usable | Frontend mock + Google Pay browser test | Pending | Unit + Browser Manual | Missing - Google Pay cancellation test | Unit PASS (reported); browser/manual simulation PENDING | Not started
W55 | Wallet authorized but confirmation response lost | Reconcile without repeating wallet nonce | Backend failure simulation | Pending | Unit + Integration | Partial - Timeout and reconciliation tests exist separately | Unit PASS (reported); DEV integration PENDING | Not started
W56 | Card tokenization fails before charge submission | No charge; safe validation error | Mocked Poynt tokenization failure | Pending | Unit | Covered - Tokenization failure test | Unit PASS (per yesterday’s Codex report; verify test results) — no live integration required | Not started
W57 | Poynt OAuth token expired or refresh fails | No incorrect decline; safe retry/reconciliation based on charge stage | Mocked OAuth failure | Pending | Unit + Integration | Partial - OAuth failure tested; token refresh not verified | Unit PASS (reported); DEV integration PENDING | Not started
W58 | Poynt returns HTTP 500 after receiving charge | Ambiguous outcome; never repost automatically | Mocked HTTP 500 after charge submission | Pending | Unit + Integration | Covered - Ambiguous HTTP response test | Unit PASS (reported); DEV integration PENDING | Not started
W59 | Payment authorized but not captured | Must not be marked SUCCEEDED for SALE | Mocked AUTHORIZED response | Pending | Unit | Covered - AUTHORIZED is not CAPTURED test | Unit PASS (per yesterday’s Codex report; verify test results) — no live integration required | Not started
W60 | Partial capture or partial approval | No full-payment finalization | Mocked partial approval | Pending | Unit | Covered - Partial capture and approval tests | Unit PASS (per yesterday’s Codex report; verify test results) — no live integration required | Not started
W61 | Poynt returns refund, void or reversal state | Must not be interpreted as successful SALE | Mocked refund/void/reversal | Pending | Unit | Covered - Refund, void and reversal tests | Unit PASS (per yesterday’s Codex report; verify test results) — no live integration required | Not started
W62 | Duplicate or inconsistent transaction lookup results | No arbitrary transaction selection | Mocked transaction lookup | Pending | Unit | Partial - Transaction correlation tests; duplicate lookup not verified | Unit PASS (per yesterday’s Codex report; verify test results) — no live integration required | Not started
W63 | Status request for a different customer | Access denied without information leakage | Authenticated API test | Pending | Integration | Covered - Wrong customer/organization authorization test | Unit PASS (reported, if applicable); DEV integration PENDING | Not started
W64 | Two concurrent submissions from separate browser tabs | No duplicate charge for same payment intent | Concurrent API request test | Pending | Integration + Browser Manual | Partial - Concurrent confirmation tested; multi-session DB test missing | Unit PASS (reported); DEV integration + browser PENDING | Not started
W65 | Google Pay unsupported browser | Wallet hidden; card remains available | Mocked SDK capability + browser check | Pending | Unit + Browser Manual | Missing - Google Pay unsupported browser test | Unit PASS (reported); browser/manual simulation PENDING | Not started